DOFT CANDLES

Diwali Pop-Up Retail Operations

Understanding & Key Deliverables

Prepared by ProMarcom Inc. for Doft Candles      |      Diwali Seasons 2026, 2027 and 2028

Date: 30 July 2026      |      For your review

1.  Purpose of this Note

This note sets out how we understand the Diwali pop-up requirement and what we will deliver as your operations partner. It is based on the parameters we agreed with your team: a compact 8x8 ft kiosk, a six-week run, and a presence across the metros and sub-metros. It also carries our suggested city list. Commercials are covered in a separate proposal.

2.  How We Understand the Requirement

Doft runs premium home-fragrance kiosks in leading malls through the Diwali season. For 2026, and with the plan to carry on in 2027 and 2028, you will run compact 8x8 ft kiosks in busy malls across the metros and sub-metros, trading for six weeks around Diwali. We handle everything on the ground, from hiring and deployment to the day-to-day running. You supply the stock, the kiosk design, the POS/EDC machines and the uniforms.

Quick summary

| Item | Details |
| --- | --- |
| Term | Diwali seasons 2026, 2027 and 2028, renewed each year |
| Operating window | Six weeks of live trading per city, across the Diwali season |
| Kiosk size | 8x8 ft (about 64 sq ft), built to your approved design |
| Backup storage | About 40 sq ft of secure storage for replenishment, or mall-provided |
| Cities | Metros and sub-metros (our suggestions are in Section 3) |
| Kiosks per city | 1 to 3, based on mall availability, footfall and your sign-off |
| Team | Full team of 12 per kiosk (see Section 5) |
| Training | One-day product and sales training by Doft, 10 to 21 days before launch, full attendance |
| You supply | Stock, kiosk design and kit, furniture, POS/EDC, uniforms (returnable) |
| We handle | Kiosk build and install, manpower, logistics, licences, daily operations and reporting |

3.  Suggested City Footprint

All locations go live within the same window. The list below sets out the cities we recommend, grouped by metro and sub-metro. The metros carry the highest premium mall footfall and festive spending, and the sub-metros listed have grown into strong premium retail markets.

Metro cities

| City | Indicative premium malls | Why |
| --- | --- | --- |
| Delhi-NCR | Select Citywalk, DLF Promenade/Emporio, Ambience | Largest premium and gifting market |
| Mumbai | Phoenix Palladium, Jio World Drive, Inorbit | High spend, strong luxury footfall |
| Bengaluru | Phoenix Mall of Asia, Orion, UB City | Young, affluent, big on home décor |
| Hyderabad | Sarath City Capital, Inorbit | Fast-growing premium retail |
| Chennai | Phoenix Marketcity, Express Avenue | Steady gifting culture |
| Kolkata | Quest, South City | Strong festive gifting market |
| Pune | Phoenix Marketcity, Amanora | Affluent, high mall engagement |

Sub-metro cities

| City | Indicative premium malls | Why |
| --- | --- | --- |
| Ahmedabad | Ahmedabad One, AlphaOne | Large, affluent, gifting-led |
| Jaipur | World Trade Park | Premium and wedding season spend |
| Chandigarh | Elante | High per-head premium retail |
| Lucknow | Phoenix Palassio | Rising luxury mall footfall |
| Kochi | Lulu Mall | Very high footfall, premium mix |
| Indore | Phoenix Citadel, C21 | Growing premium spend |
| Surat | VR Surat | High income, gifting-oriented |

These mall names are only indicative. We will confirm the final list against live availability, footfall, category fit and licence cost. We advise confirming the city list early, since premium Diwali slots fill up quickly.

4.  What We Will Deliver

We will run the workstreams below, each to your brand standards and the mall's compliance rules.

| Workstream | What we deliver |
| --- | --- |
| 1. Kiosk build & install | - Build and install the 8x8 kiosk to your approved design - Transport, setup, upkeep, dismantling and return of fixtures - A 3-day buffer before go-live to cover any build delay |
| 2. Mall coordination & legal | - Liaison with mall management through the season - All permissions, licences, documents and compliance - Electricity, access passes, loading/unloading and operational approvals |
| 3. Logistics & replenishment | - Pick up and move stock from your Ghaziabad warehouse - Refill on time from local storage, with reorder levels set per SKU - Safe handling, stock control, and return of unsold stock with reconciliation |
| 4. Recruitment & staffing | - Sourcing, background checks, deployment and attendance - Payroll and full statutory compliance for all staff - Same-day replacement of any absent or resigned staff, at no extra cost |
| 5. Training support | - Get full attendance at your one-day product and sales training - Keep trained staff on through the season, and train any replacements |
| 6. Store operations | - Daily open and close, sales and customer service - Cash handling and POS/EDC, plus visual merchandising and cleanliness - Stock reconciliation, and compliance with mall and Doft standards |
| 7. Reporting | - Daily numbers on sales, footfall, stock, replenishment and attendance - Customer feedback and a log of any operational issues - Weekly city reviews and a full reconciliation at the end of the season |

5.  Team Per Kiosk

We will deploy the full team specified in the brief at every kiosk: twelve people covering sales, support, cash handling, housekeeping and transport, led by a Team Leader who is a permanent ProMarcom employee. Alongside this, we will hold a trained bench of about 15% per city, so any absence is covered the same day at no extra cost to you.

| Role | Per kiosk | Notes |
| --- | --- | --- |
| Sales Executives | 6 | Female, 22-25, fluent English, retail sales experience |
| Sales Support Staff | 2 | Merchandising, stock handling and queue management |
| Helper | 1 | Housekeeping and material handling |
| Cashier | 1 | Experienced on POS/EDC machines |
| Driver | 1 | Stock transport and replenishment runs |
| Team Leader / Manager | 1 | Permanent ProMarcom employee who runs the kiosk |
| Total per kiosk | 12 | Plus a trained bench of about 15% per city for quick cover |

6.  Indicative Timeline

The plan below is shown relative to go-live (T), with a six-week trading window. All locations launch together in the same window, so the same plan applies to every city in parallel. Exact calendar dates are fixed once malls are confirmed.

| Activity | Timing | Owner |
| --- | --- | --- |
| Contract award and kick-off | T minus 8 weeks | Doft + ProMarcom |
| Mall shortlisting and licence applications | T minus 7 to 4 weeks | ProMarcom |
| Recruitment and background checks | T minus 6 to 2 weeks | ProMarcom |
| Kiosk fabrication and fit-out | T minus 3 to 1 weeks | ProMarcom |
| Doft product and sales training (1 day) | T minus 2 weeks | Doft |
| Stock pickup from Ghaziabad and first fill | T minus 1 week | ProMarcom |
| Go-live and daily operations (6 weeks) | T to T plus 6 weeks | ProMarcom |
| Dismantle, fixture and unsold-stock return | T plus 6 to 7 weeks | ProMarcom |
| Final reconciliation and season review | T plus 7 weeks | Doft + ProMarcom |

A live project timeline and per-city Gantt are maintained in the operations workbook and shared with your team.

7.  Reporting & Reviews

You will get a standard daily report per kiosk, pulled together by city. It covers:

- Sales: units, gross, discounts, net, bills and average bill value

- Footfall and conversion: walk-ins, engaged, bills and conversion rate

- Stock and replenishment: opening, received, sold, closing and reorder flags

- Attendance: present, absent and attendance rate

- Customer feedback and any operational issues

Beyond the daily report, we will hold a weekly review call per city and a full reconciliation at the end of the season. A live operations workbook covering staffing, budget, timeline and trackers runs alongside the programme.

8.  Our Commitments

- Full attendance at your training, and equally trained staff on the floor at all times.

- Same-day replacement of any absent or resigned staff, at no extra cost to you.

- Uniforms kept washed, ironed and in good shape, and returned in good condition.

- Compliance signed off before every go-live: licences, GST and e-invoicing, PF and ESIC, insurance, fire and electrical, and staff background checks.

- The same service quality and brand standards across every city, even when several run at once.

9.  What You Provide, and a Few Assumptions

- You supply the stock, the kiosk design and kit, the furniture (unless we agree otherwise), the POS/EDC machines and the uniforms (returnable).

- Stock is picked up from your Ghaziabad warehouse. We take care of insurance in transit and safe handling.

- If we pay any mall licence or space fees, we will bill them as a pass-through unless we agree otherwise. We will confirm this mall by mall.

- We will finalise the cities, malls, kiosk counts and go-live dates with you before each season.

10.  Next Steps

- You confirm the final city list, so we can lock premium mall slots early.

- We shortlist specific malls with availability, footfall and licence cost.

- We agree the kiosk count per city, the go-live dates and the training schedule.

- We finalise commercials in a separate proposal and sign the agreement.

Prepared by ProMarcom Inc. (EventsActive). City and mall suggestions are indicative and will be confirmed with you.