## 1. README & Assumptions
Doft Candles — Diwali Pop-Up Retail Operations
ProMarcom Inc. ¦ Operations & Costing Workbook ¦ Seasons 2026 / 2027 / 2028
PURPOSE
This workbook is the operational and commercial toolkit for managing Doft Candles' seasonal Diwali pop-up kiosks. It contains the staffing model, cost/budget build-up, project timeline, and all daily-reporting, compliance and tracking templates required by the client brief.
HOW TO USE
Gold cells | Inputs you edit — rates, counts, dates, actuals.
White cells | Formula-driven — do not overwrite; they recalculate automatically.
Green cells | Roll-up / summary totals.
GLOBAL ASSUMPTIONS (edit these — they drive every other sheet)
Number of cities / regions | 3 | Brief: multi-city. Model default — edit as awarded.
Pop-ups per region | 3 | Brief: 2–4 per region. Mid-point used.
Total pop-ups (calc) |  | Cities × pop-ups per region.
Operational duration (weeks) | 4 | Brief: 3–5 weeks before Diwali.
Setup / fabrication (days) | 5 | Kiosk install + fit-out before go-live.
Training window (days before go-live) | 14 | Brief: training 10–21 days prior.
Staff per pop-up | 12 | Fixed by brief (see Staffing Plan tab).
Operating days per week | 7 | Mall hours, all days.
Store hours per day | 11 | Typical mall trading hours.
Statutory load on wages (PF+ESI+etc.) | 13% | ~13% employer statutory contribution.
Contractor management margin | 15% | Applied on total direct cost.
GST on contractor invoice | 18% | Output GST, 18%.
Currency | INR (₹) | All figures in Indian Rupees.
DISCLAIMER
All pay rates and cost figures are realistic planning placeholders, not quotations. Confirm against actual vendor quotes, mall licence fees, and statutory rates before commercial submission.

## 2. Project Timeline
Project Timeline & Milestones
Per-region rollout — T = kiosk go-live (Diwali season). Weeks shown relative to go-live.
# | Phase / Activity | Owner | Start (T-) | End (T-) | T-6w | T-5w | T-4w | T-3w | T-2w | T-1w
1 | Contract award & kick-off | Doft + Contractor | T-8w | T-7w
2 | Mall shortlisting & licence applications | Contractor | T-7w | T-4w
3 | Kiosk fabrication & fit-out (Doft-approved design) | Contractor | T-3w | T-1w
4 | Recruitment & background verification | Contractor | T-6w | T-2w
5 | Doft product & sales training (1 day, 100% attendance) | Doft | T-2w | T-2w
6 | Statutory registration & staff onboarding/payroll setup | Contractor | T-4w | T-1w
7 | Stock pickup from Ghaziabad warehouse & first fill | Contractor | T-1w | T-1w
8 | Store go-live & daily operations (3–5 weeks) | Contractor | T | T+5w
9 | Daily reporting (sales/footfall/inventory/attendance) | Contractor | T | T+5w
10 | Replenishment cycles | Contractor | T | T+5w
11 | Dismantling, fixture return & unsold-stock return | Contractor | T+5w | T+6w
12 | Final reconciliation & season review | Both | T+6w | T+6w

## 3. Staffing Plan
Staffing Plan — Per Pop-Up
Fixed composition per the brief: 12 personnel per kiosk.
Role | Headcount | Gender / Profile | Key Requirement | Reports To | Employment
Sales Executive | 6 | Female, 22–25 yrs | Fluent conversational English + retail sales experience | Team Leader | ProMarcom payroll
Sales Support Staff | 2 | Any | Merchandising, stock handling, queue mgmt | Team Leader | ProMarcom payroll
Helper | 1 | Any | Housekeeping, material handling | Team Leader | ProMarcom payroll
Cashier | 1 | Any | Experienced with POS/EDC machines | Team Leader | ProMarcom payroll
Driver | 1 | Any | Valid licence; stock transport & runs | Team Leader | ProMarcom payroll
Team Leader / Manager | 1 | Any | Daily operations owner | Contractor Ops Head | Permanent employee of contractor
TOTAL PER POP-UP
Attrition rule (brief): any attrition after training or during operations must be replaced immediately with equally-trained personnel at no additional cost. Maintain a trained bench — see Recruitment Tracker.

## 4. Manpower Cost
Manpower Cost Build-Up
Per pop-up monthly cost × duration, then rolled up to all pop-ups.
Role | Headcount | Monthly CTC (₹) | Statutory Load | Loaded Monthly (₹) | Months | Cost / Pop-up (₹)
Sales Executive | 6 | 22000
Sales Support Staff | 2 | 16000
Helper | 1 | 14000
Cashier | 1 | 20000
Driver | 1 | 18000
Team Leader / Manager | 1 | 35000
TOTAL PER POP-UP
Number of pop-ups
TOTAL MANPOWER COST (all pop-ups)
Note: 'Months' includes ~2 extra weeks covering setup, training and buffer. Edit CTC (gold) to your actual pay bands.

## 5. Budget Summary
Budget Summary — Full Engagement
All cost heads. Per-pop-up inputs (gold) roll up by total pop-up count.
Cost Head | Basis | Per Pop-up (₹) | Pop-ups | Total (₹) | Notes
Manpower (loaded, full duration) | From Manpower Cost tab |  |  |  | 6 SE + 2 SS + Helper + Cashier + Driver + TL
Kiosk fabrication, fit-out & signage | Per pop-up | 180000 |  |  | On-site fabrication of Doft-approved design
Kiosk transport, install & dismantle | Per pop-up | 45000 |  |  | To/from mall, both ways
Mall licence / space fee (if borne) | Per pop-up | 250000 |  |  | Confirm per mall — often reimbursed by Doft
Electricity / utilities & access passes | Per pop-up | 25000 |  |  | Mall charges for the period
Stockroom (~90 sq ft) rent | Per pop-up | 40000 |  |  | Replenishment store
Logistics — Ghaziabad pickup & replenishment | Per pop-up | 60000 |  |  | Vehicle, fuel, driver runs
Uniform upkeep (wash/iron/maintain) | Per pop-up | 12000 |  |  | Uniforms supplied by Doft; upkeep by contractor
Staff welfare (meals/transport/incentives) | Per pop-up | 55000 |  |  | Attendance & sales incentives
Statutory & compliance filing | Per pop-up | 20000 |  |  | Licences, registrations, insurance
Training logistics support | Per pop-up | 15000 |  |  | Venue coordination, travel for training day
Contingency / attrition replacement buffer | Per pop-up | 30000 |  |  | Bench & immediate replacement
DIRECT COST SUBTOTAL
Contractor management margin
CONTRACT VALUE (pre-GST)
GST
TOTAL CONTRACT VALUE (incl. GST)

## 6. Recruitment Tracker
Recruitment & Deployment Tracker
One row per candidate. Track from sourcing through background verification, training and deployment.
Candidate | Role | City | Pop-up ID | Phone | Sourced On | BGV Status | Training Done | Deployment Status | Bench (Y/N) | Remarks
Priya Sharma | Sales Executive | Delhi | DEL-01 | 98xxxxxx01 | 2026-09-20 | Verified | Yes | Deployed | N | Star performer prior season
Note on A5: Example row — delete or overwrite. Fill one row per record.

## 7. Attendance Tracker
Daily Staff Attendance Tracker
Mark P (Present) / A (Absent) / L (Leave) / R (Replaced). One row per staff member.
Staff Name | Role | Pop-up ID | D1 | D2 | D3 | D4 | D5 | D6 | D7 | Present | % Attendance
Priya Sharma | Sales Exec | DEL-01 | P | P | P | A | P | P | P

## 8. Daily Sales Report
Daily Sales Report
One row per pop-up per day. Feeds the season sales roll-up at the bottom.
Date | City | Pop-up ID | Units Sold | Gross Sales (₹) | Discounts (₹) | Net Sales (₹) | Bills | Avg Bill (₹) | Reported By
2026-10-15 | Delhi | DEL-01 | 42 | 168000 | 8000 |  | 38 |  | R. Verma
SEASON TOTAL

## 9. Inventory & Replenish
Inventory & Stock Replenishment
SKU-level daily reconciliation per pop-up. Closing = Opening + Received − Sold − Damaged.
Date | Pop-up ID | SKU / Product | Opening | Received | Sold | Damaged | Closing | Reorder Level | Reorder?
2026-10-15 | DEL-01 | Rose Petal 200g | 60 | 24 | 42 | 0 |  | 20
Note on A5: Example row — delete or overwrite. Fill one row per record.

## 10. Footfall & Conversion
Footfall & Conversion
Daily footfall vs bills. Conversion = Bills / Footfall.
Date | City | Pop-up ID | Footfall | Walk-ins Engaged | Bills | Conversion % | Reported By
2026-10-15 | Delhi | DEL-01 | 520 | 180 | 38 |  | R. Verma

## 11. Customer Feedback
Customer Feedback Log
Capture verbatim customer feedback and resolution. Feeds Doft brand & product insights.
Date | City | Pop-up ID | Customer | Rating (1-5) | Category | Feedback | Action Taken | Status
2026-10-15 | Delhi | DEL-01 | Walk-in | 5 | Fragrance | Loved the sandalwood range | Recommended gift set | Closed
Note on A5: Example row — delete or overwrite. Fill one row per record.

## 12. Compliance Checklist
Compliance & Legal Checklist
Per pop-up. Status: Not Started / In Progress / Done / N/A.
# | Requirement | Responsible | Due (T-) | Status | Remarks
1 | Mall space licence agreement signed
2 | Shops & Establishment / trade compliance
3 | GST registration & e-invoicing ready
4 | Staff police / background verification (BGV) complete
5 | PF & ESIC registration for deployed staff
6 | Public liability / event insurance in place
7 | Fire & safety and electrical clearance
8 | Access passes & loading/unloading permits
9 | Electricity connection / DG arrangement
10 | POS/EDC machine received & tested
11 | Uniforms received (returnable) & logged
12 | Stock receipt & insurance-in-transit from Ghaziabad
13 | Labour law / minimum-wage compliance
14 | Signed attendance & payroll process
15 | Dismantling & fixture-return sign-off plan

## 13. Risk Register
Risk Register
Score = Likelihood × Impact (1-5 each). Mitigate high scores first.
# | Risk | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Owner
1 | Staff attrition after training | 4 | 4 |  | Maintain 15% trained bench; immediate no-cost replacement | Ops Head
2 | Mall licence / permission delay | 3 | 5 |  | Start licensing at T-7w; parallel mall shortlist | Legal
3 | Stock-out during peak days | 3 | 5 |  | Reorder levels + daily replenishment from 90 sq ft stockroom | Logistics
4 | POS/EDC downtime | 2 | 4 |  | Backup EDC + trained cashier; mall Wi-Fi + dongle failover | Cashier/IT
5 | Underperformance vs sales target | 3 | 4 |  | Daily reporting, incentives, TL coaching | Team Leader
6 | Kiosk fabrication delay | 2 | 5 |  | Vendor SLA + 3-day buffer before go-live | Projects
7 | Statutory non-compliance | 2 | 5 |  | Compliance checklist sign-off before go-live | Legal
8 | Cash handling / shrinkage | 2 | 4 |  | Dual control, daily reconciliation, CCTV where available | Cashier/TL
9 | Uniform damage / loss | 2 | 2 |  | Issue log, upkeep SOP, deposit control | Team Leader